## Sheet1
Date | Hours | Category | Task | Jira Issue | Sprint | Notes
2026-07-06 | 3 | Project Management | GitHub setup, directory structure | NA
2026-07-07 | 2 | Project Management | LICENSE | NA
2026-07-10 | 3 | Research | research revenue, lesson ideas, retention | NA
2026-07-11 | 2 | Research | watched Jira tutorials and began setup with cusomizations | NA
2026-07-13 | 2 | Project Management | set up Jira Sprint 1 backlog | NA
2026-07-13 | 1 | Docuemtation | created Project Schedule and Time Log | NA
2026-07-15 | 2 | Docuemtation | Begin Project Charter | KAN-6 | yek Sprint 1
2026-07-15 | 1 | Project Management | Notion documentation board setup | NA
2026-07-16 | 6 | Docuemtation | Multiple initiation and planning documents completed | NA | yek Sprint 1
2026-07-16 | 1 | Project Management | general Notion, Jira, and directory structure | NA
2026-07-20 | 3 | Docuemtation | finalized Vision Doc and Business Case doc | KAN-21, KAN-24 | yek Sprint 1
2026-07-20 | 1 | Project Management | decision to modify docs to include PM docs as co-primary project objective | NA
2026-07-21 | 2 | Docuemtation | finalize Pro-Scope-Stmt, began outline for PRD | KAN-10, KAN-13 | yek Sprint 1
2026-07-26 | 6 | Docuemtation | mostly the PRD Func Requirements | NA | yek Sprint 1
2026-07-26 | 2 | Project Management | Jira Stories and tasks from the PRD | NA | yek Sprint 1
2026-08-08 | 3 | Project Management | Sprint Review, Restrospective, Planning | NA
2026-08-09 | 1 | Docuemtation | Software Architecture Document | KAN-60 | yek Sprint 2
2026-08-09 | 1 | Research | general JSON formatting | NA
2026-08-10 | 4 | Docuemtation | decision log needs backfilled | KAN-59 | yek Sprint 2
2026-08-10 | 1 | Research | general category and vocab overview | NA
2026-08-29 | 4 | Docuemtation | WBS, Risk Register, Roadmap | KAN-22, KAN-15, KAN-14 | yek Sprint 2
2026-08-29 | 4 | Research | LLC research | NA
2026-09-05 | 2 | Project Management | Sprint Review, Restrospective, Planning | NA
2026-09-06 | 3 | Docuemtation | Accessibility Document | KAN-72 | yek Sprint 3
2026-09-07 | 3 | Marketing | created accounts for various social media | NA
2026-09-08 | 6 | Website | Porkbun domain sync with GitHub pages | NA
2026-09-09 | 2 | Marketing | Studying Google Analytics and setting up Brevo | NA
2026-09-09 | 2 | Website | Adding cotent and style to website homepage | NA
total hours | 73
Category | Description
Documentation | Writing project documents
Flutter Development | Coding
UI/UX Design | Wireframes and interface
Database | Firebase, JSON, schema
Testing | Manual and automated testing
Research | Learning Flutter, APIs, reading documentation
Project Management | Jira, scheduling, meetings, planning
Website | Squarespace portfolio
Marketing | YouTube, templates, blog posts