## Sheet1
WBS | Phase / Activity | Duration | Dependency | Sprint | Milestone | Planned Start Date | Actual Start Date | Planned Finish | Actual Finish | Status
1 | Project Initiation | 3 weeks | — | Sprint 1 |  | 2026-07-12 | 2026-07-12 | 2026-08-01 | 2026-08-01 | Complete
1.1 | Vision Statement | 1 day | — | Sprint 1 |  | 2026-07-16 | 2026-07-16 | 2026-08-01 | 2026-08-01 | Complete
1.2 | Vision Document | 2 days | 1.1 | Sprint 1 |  | 2026-07-16 | 2026-07-16 | 2026-08-01 | 2026-08-01 | Complete
1.3 | Project Charter | 2 days | 1.2 | Sprint 1 |  | 2026-07-15 | 2026-07-15 | 2026-08-01 | 2026-08-01 | Complete
1.4 | Business Case | 3 days | 1.3 | Sprint 1 |  | 2026-07-16 | 2026-07-16 | 2026-08-01 | 2026-08-01 | Complete
1.5 | Stakeholder Register | 1 day | 1.3 | Sprint 1 |  | 2026-07-15 | 2026-07-15 | 2026-08-01 | 2026-08-01 | Complete
1.6 | Initiation Complete | 0 days | 1.5 | Sprint 1 | ✔ | 2026-07-12 | 2026-07-12 | 2026-08-01 | 2026-08-01 | Complete
2 | Project Planning | 6 weeks | 1.5 | Sprints 2–3 |  | 2026-08-02 | 2026-08-09 | 2026-10-17 |  | In-Progress
2.1 | Scope Statement | 3 days | 1.5 | Sprint 2 |  | 2026-07-15 | 2026-07-15 | 2026-08-01 | 2026-08-01 | Complete
2.2 | Product Requirements Document | 1 week | 2.1 | Sprint 2 |  | 2026-07-12 | 2026-07-12 | 2026-08-01 |  | In-Progress
2.3 | Work Breakdown Structure | 3 days | 2.2 | Sprint 2 |  | 2026-08-09 |  | 2026-08-29 | 2026-08-29 | Complete
2.4 | Risk Register | 2 days | 2.2 | Sprint 2 |  | 2026-08-09 | 2026-08-09 | 2026-08-29 | 2026-08-29 | Complete
2.5 | Architecture Design | 1 week | 2.2 | Sprint 2 |  | 2026-08-09 | 2026-08-09 | 2026-08-29 | 2026-08-29 | Complete
2.6 | Communication Plan | 2 days | 2.3 | Sprint 2 |  | 2026-07-16 | 2026-07-16 | 2026-08-01 | 2026-08-01 | Complete
2.7 | UI Wireframes | 3 weeks | 2.6 | Sprint 3-4 |  | 2026-08-30 |  | 2026-10-17 |  | To-Do
2.8 | Planning Complete | 0 days | 2.7 | Sprint 3-4 | ✔ | 2026-08-09 |  | 2026-10-17 |  | To-Do
3 | Development | 12 weeks | 2.8 | Sprints 5-8 |  | 2026-10-18 |  | 2027-01-09 |  | To-Do
3.1 | Flutter Project Setup | 2 weeks | 2.8 | Sprint 5 |  | 2026-10-18 |  | 2026-11-07 |  | To-Do
3.2 | Authentication | 2 weeks | 3.1 | Sprint 5 |  | 2026-10-18 |  | 2026-11-07 |  | To-Do
3.3 | Flashcard Engine | 3 weeks | 3.2 | Sprint 6 |  | 2028-11-08 |  | 2026-11-28 |  | To-Do
3.4 | JSON Data Integration | 3 weeks | 3.3 | Sprint 7 |  | 2026-11-29 |  | 2026-12-19 |  | To-Do
3.5 | Audio Pronunciation | 3 weeks | 3.4 | Sprint 7 |  | 2026-11-29 |  | 2026-12-19 |  | To-Do
3.6 | Statistics Dashboard | 2 weeks | 3.5 | Sprint 8 |  | 2026-12-20 |  | 2027-01-09 |  | To-Do
3.7 | Settings & Preferences | 1 week | 3.6 | Sprint 8 |  | 2026-12-20 |  | 2027-01-09 |  | To-Do
3.8 | Ads & Premium Features | 2 weeks | 3.7 | Sprint 8 |  | 2026-12-20 |  | 2027-01-09 |  | To-Do
3.9 | MVP Complete | 0 days | 3.8 | Sprint 8 | ✔ | 2026-09-20 |  | 2027-01-09 |  | To-Do
4 | Testing | 3 weeks | 3.9 | Sprint 9 |  | 2027-01-10 |  | 2027-01-30 |  | To-Do
4.1 | Unit Testing | 2 weeks | 3.9 | Sprint 9 | [5 empty] | To-Do
4.2 | Widget Testing | 1 week | 4.1 | Sprint 9 | [5 empty] | To-Do
4.3 | Beta Testing | 2 weeks | 4.2 | Sprint 9 | [5 empty] | To-Do
4.4 | Bug Fixes | 1 week | 4.3 | Sprint 9 | [5 empty] | To-Do
4.5 | Testing Complete | 0 days | 4.4 | Sprint 9 | ✔ |  |  |  |  | To-Do
5 | Deployment | 3 weeks | 4.5 | Sprint 10 |  | 2027-01-31 |  | 2027-02-20 |  | To-Do
5.1 | App Store Preparation | 1 week | 4.5 | Sprint 10 | [5 empty] | To-Do
5.2 | Publish Website | 2 days | 5.1 | Sprint 10 | [5 empty] | To-Do
5.3 | Publish GitHub Documentation | 2 days | 5.1 | Sprint 10 | [5 empty] | To-Do
5.4 | Submit to App Stores | 3 days | 5.3 | Sprint 10 | [5 empty] | To-Do
5.5 | Version 1.0 Released | 0 days | 5.4 | Sprint 10 | 🚀 |  |  |  |  | To-Do

## Sheet2
Sprint 1 | 2026-07-12 | 2026-08-01
Sprint 2 | 2026-08-09 | 2026-08-29
Sprint 3 | 2026-09-06 | 2026-09-26
Sprint 4 | 2026-09-27 | 2026-10-17
Sprint 5 | 2026-10-18 | 2026-11-07
Sprint 6 | 2026-11-08 | 2026-11-28
Sprint 7 | 2026-11-29 | 2026-12-19
Sprint 8 | 2026-12-20 | 2027-01-09
Sprint 9 | 2027-01-10 | 2027-01-30
Sprint 10 | 2027-01-31 | 2027-02-20
Sprint 11 | 2027-02-21 | 2027-03-13
Sprint 12 | 2027-03-14 | 2026-04-03
Sprint 13 | 2026-04-04 | 2027-04-24
Sprint 14 | 2027-04-25 | 2027-05-15