## Untitled 3b946ee4b62680ed94afc1
ID | Risk | Probability | Impact | Risk Score | Mitigation / Preventive Action | Contingency | Risk Response | Category | Owner | Status
R-001 | Project takes significantly longer than planned | High | High | 9 | Maintain realistic Sprint commitments and prioritize MVP requirements | Delay launch and move lower-priority features to backlog | Mitigate | Schedule | Project Manager | Open
R-002 | Limited ~10 hours/week availability slows development | High | High | 9 | Estimate work using available weekly capacity rather than ideal development time | Extend Sprint or overall project timeline | Mitigate | Schedule | Project Manager | Open
R-003 | Scope expands beyond the original MVP | High | High | 9 | Require new features to be evaluated before adding them to committed scope | Move feature to Product Backlog / future release | Mitigate | Scope | Project Manager | Open
R-004 | Learning Flutter/Dart takes longer than expected | High | Medium | 6 | Allocate dedicated learning time and build features incrementally | Simplify implementation or postpone advanced feature | Mitigate | Technical | Project Manager | Open
R-005 | Insufficient Flutter/Dart knowledge causes implementation errors | Medium | Medium | 4 | Follow Flutter/Dart learning resources and document technical decisions | Refactor affected code or simplify design | Mitigate | Technical | Developer | Open
R-006 | UI/UX design takes longer due to limited prior experience | High | Medium | 6 | Use established design systems, templates, wireframes, and mockups | Reduce visual complexity for MVP | Mitigate | Schedule / Technical | Project Manager / Developer | Open
R-007 | UI design does not provide an intuitive learning experience | Medium | High | 6 | Create wireframes and prototypes before implementation; perform informal usability review | Revise affected screens after testing | Mitigate | Product | Project Manager | Open
R-008 | Vocabulary content takes longer to create than expected | High | Medium | 6 | Maintain a Vocabulary Master spreadsheet and review categories systematically | Reduce initial vocabulary count or defer categories | Mitigate | Content | Content Owner | Open
R-009 | Farsi translations contain errors or unnatural wording | Medium | High | 6 | Have translations reviewed by a native Farsi speaker before release | Correct translations in content files and issue a content update | Mitigate | Content | Content Owner | Open
R-010 | Vocabulary categories contain inappropriate, redundant, or low-value words | Medium | Medium | 4 | Review vocabulary list before generating production JSON | Remove or replace low-value vocabulary | Mitigate | Content | Content Owner | Open
R-011 | English and Farsi vocabulary IDs become mismatched | Medium | High | 6 | Maintain globally unique IDs and use the Vocabulary Master as the source of truth | Reconcile JSON files against master spreadsheet | Mitigate | Data / Technical | Developer | Open
R-012 | Duplicate vocabulary IDs are introduced | Low | High | 3 | Validate IDs before generating JSON | Correct duplicates before release | Mitigate | Data | Developer | Open
R-013 | JSON formatting or schema errors prevent content from loading | Medium | High | 6 | Validate JSON and test loading after content changes | Restore last known-good JSON version | Mitigate | Technical | Developer | Open
R-014 | Audio files are incorrectly named or associated with vocabulary | Medium | Medium | 4 | Use vocabulary IDs as filenames and language-specific folders | Re-record/rename affected files | Mitigate | Technical / Content | Developer | Open
R-015 | Audio recordings have inconsistent pronunciation or quality | Medium | Medium | 4 | Establish recording standards before recording large batches | Re-record unacceptable files | Mitigate | Content | Content Owner | Open
R-016 | Audio production takes significantly longer than expected | High | Medium | 6 | Record in organized batches and track recording status | Release initial version with fewer audio files if necessary | Mitigate | Schedule | Project Manager | Open
R-017 | Offline functionality conflicts with advertising requirements | Medium | High | 6 | Define clearly which features require connectivity and test offline/online states | Limit advertising when offline or adjust monetization approach | Mitigate | Technical / Business | Developer | Open
R-018 | Advertising revenue is too low to justify implementation complexity | Medium | Medium | 4 | Track ad impressions, engagement, and revenue after launch | Reduce ads or emphasize premium monetization | Accept / Mitigate | Business | Product Owner | Open
R-019 | Premium monetization produces insufficient revenue | Medium | Medium | 4 | Test pricing and conversion assumptions after launch | Adjust pricing/features or remain primarily ad-supported | Accept / Mitigate | Business | Product Owner | Open
R-020 | User Accounts are eventually needed for features originally designed without accounts | Medium | High | 6 | Design local functionality so account integration could be added later | Introduce account system in a future release | Accept / Mitigate | Scope / Technical | Product Owner | Open
R-021 | Statistics cannot be synchronized across devices without User Accounts | Medium | Medium | 4 | Clearly define statistics as local/offline unless account functionality is added | Add optional accounts/cloud synchronization later | Accept | Technical / Product | Developer | Open
R-022 | Device-specific purchase restoration becomes difficult without User Accounts | Medium | High | 6 | Use the platform's purchase restoration mechanisms rather than creating custom accounts | Add account infrastructure if future requirements justify it | Mitigate | Monetization / Technical | Developer | Open
R-023 | App performance is poor on older devices | Medium | Medium | 4 | Keep initial architecture lightweight and test on multiple devices | Optimize or reduce resource-intensive features | Mitigate | Technical | Developer | Open
R-024 | App storage requirements become excessive due to audio files | Medium | Medium | 4 | Compress/optimize audio and monitor total asset size | Reduce audio quality/coverage or offer downloadable audio packages | Mitigate | Technical | Developer | Open
R-025 | GitHub repository becomes difficult to manage as audio/content grows | Medium | Medium | 4 | Establish organized asset directories and naming conventions | Reevaluate asset hosting strategy | Mitigate | Technical | Developer | Open
R-026 | Public repository exposes unfinished or confusing project materials | Medium | Medium | 4 | Establish documentation structure and review public-facing content | Remove/archive confusing material | Mitigate | Reputation / Portfolio | Project Manager | Open
R-027 | PM documentation becomes so extensive that it slows application development | Medium | Medium | 4 | Allocate documentation time and prioritize artifacts that demonstrate meaningful PM practices | Defer low-value documentation | Mitigate | Scope / Schedule | Project Manager | Open
R-028 | PM documentation becomes inconsistent with actual project execution | Medium | High | 6 | Update documentation at Sprint boundaries and record decisions as they occur | Reconcile documentation retrospectively | Mitigate | Documentation | Project Manager | Open
R-029 | Jira, Notion, GitHub, and other tools create duplicated information | Medium | Medium | 4 | Define a system of record for each type of information | Consolidate redundant information | Mitigate | Process | Project Manager | Open
R-030 | Requirements are not traceable through development and testing | Medium | High | 6 | Assign unique FR IDs and map requirements to Jira Stories and testing | Perform requirements reconciliation before release | Mitigate | Requirements | Project Manager | Open
R-031 | Requirements change after development has already begun | High | Medium | 6 | Use backlog prioritization and formal change decisions | Reprioritize future Sprint work | Mitigate | Requirements | Project Manager | Open
R-032 | Testing is insufficient before launch | Medium | High | 6 | Create test cases and test major user flows before release | Delay launch until critical defects are resolved | Mitigate | Quality | Developer | Open
R-033 | Critical bugs remain undiscovered until after launch | Medium | High | 6 | Conduct incremental testing throughout development rather than only at the end | Release hotfix and prioritize defect resolution | Mitigate | Quality | Developer | Open
R-034 | App Store / Google Play submission requirements cause launch delays | Medium | High | 6 | Review store requirements well before launch | Delay launch or adjust release schedule | Mitigate | Release | Project Manager | Open
R-035 | Launch target of January 1, 2027 cannot be achieved | Medium | High | 6 | Track schedule variance and prioritize MVP functionality | Delay launch rather than releasing an unstable product | Mitigate | Schedule | Project Manager | Open
R-036 | Lack of advertising limits initial user acquisition | High | Medium | 6 | Use free/low-cost channels and test a small paid advertising budget | Increase marketing investment if early metrics justify it | Accept / Mitigate | Marketing | Product Owner | Open
R-037 | Paid advertising produces poor return on investment | Medium | Medium | 4 | Start with a small experimental budget and track acquisition metrics | Stop ineffective campaigns | Mitigate | Marketing | Product Owner | Open
R-038 | User retention is lower than expected | High | High | 9 | Monitor retention, engagement, and feature usage after launch | Prioritize retention improvements in subsequent releases | Mitigate | Product / Business | Product Owner | Open
R-039 | Initial download volume is substantially below expectations | Medium | Medium | 4 | Set realistic expectations and establish low-cost marketing channels | Increase promotion or revise product positioning | Accept / Mitigate | Business | Product Owner | Open
R-040 | App receives downloads but users do not regularly use it | High | High | 9 | Monitor DAU/retention and evaluate onboarding and learning experience | Improve onboarding, content, and engagement features | Mitigate | Product | Product Owner | Open
R-041 | Monetization negatively affects the learning experience | Medium | High | 6 | Keep advertising unobtrusive and evaluate user feedback | Reduce advertising or adjust premium strategy | Mitigate | Product / Business | Product Owner | Open
R-042 | Project expenses exceed the planned budget | Medium | Medium | 4 | Maintain detailed expense log and review budget periodically | Reduce discretionary spending | Mitigate | Financial | Project Manager | Open
R-043 | Unexpected professional/consulting costs arise | Low | Medium | 2 | Include contingency allowance in project budget | Defer optional consulting | Accept / Mitigate | Financial | Project Manager | Open
R-044 | Legal/licensing issue arises with third-party assets | Low | High | 3 | Track asset sources and licensing requirements | Replace affected asset | Mitigate | Legal | Project Manager | Open
R-045 | Project documentation or code is accidentally lost | Low | High | 3 | Use Git version control and maintain backups | Restore from repository/backup | Mitigate | Technical / Project | Project Manager | Open
R-046 | Future language expansion requires architectural changes | Medium | High | 6 | Use language-separated JSON files and shared vocabulary IDs from the beginning | Refactor data layer before expansion | Mitigate | Architecture | Developer | Open
R-047 | Adding too many languages/content categories increases maintenance burden | Medium | Medium | 4 | Treat additional languages as future releases rather than MVP commitments | Limit supported languages/categories | Mitigate | Scope / Architecture | Product Owner | Open
R-048 | Personal motivation decreases during the long development process | Medium | Medium | 4 | Maintain achievable Sprint goals and track visible progress | Reduce scope and prioritize a minimum viable release | Mitigate | Project | Project Manager | Open
R-049 | The project becomes primarily a PM documentation exercise rather than a functioning application | Medium | High | 6 | Maintain separate development and documentation goals and prioritize functional milestones | Temporarily reduce documentation effort to complete MVP | Mitigate | Strategic | Project Manager | Open
R-050 | The project becomes too technically ambitious for a learning project | High | High | 9 | Maintain MVP boundaries and defer advanced features | Remove/defer advanced features until core app is stable | Mitigate | Strategic / Technical | Project Manager | Open